## Purpose
Refer to the NSR Process Dictionary located on the RDM SharePoint site for detailed guidance which includes the high level responsibilities for ALL participants in the NSR process.
The following links should be used for RA Analyst guidance for other types of NSRs:
iEHR Information Exchange (IE)
Connected Health (Mobile Applications)
Date: | 2016-10-12
Process Guide for Requirements Development and Management (RDM) Analysts
Overview:
This document highlights the steps Requirements Analysis (RA) Analysts should complete when processing a "traditional" New Service Request (NSR) in the Level 0 (Initiation), Level 1 (Assessment), and Level 2 (Analysis) Phases. This applies only to those NSRs that are not currently “projects” (or are very close to being deemed a “project”). RDM has not been asked to backfill a Business Requirements Document (BRD) to support predetermined Office of Information and Technology (OI&T) development plans or Business Owners’ solutions.

## General NSRD Hints
Compressed/Zip Folders (Creating) | At times, multiple documents will need to be placed in a single link. These documents will need to be compressed into a zip file before uploading into the New Service Request Database (NSRD). Right-click on your desktop and select New Compressed (Zip) Folder. After saving the documents to the local computer, drag and drop the files into this compressed folder. After all documents are loaded, proceed with NSRD upload.
Compressed/Zip Folders (Updating) | Before adding new documents to the compressed/zip folder previously uploaded to the NSRD, save it to the local computer. Then, add new documents. Once the new documents have been added, upload the compressed folder back to the NSRD.
NSRD Comments (External) | Use this option for comments that you want viewable by everyone.
NSRD Comments (Internal) | Use this option for comments that you do not want to share outside of Requirements Development & Management (RDM).
NSRD Comments (Weekly) | When actively working on a request, comments should be entered weekly (at a minimum).
On Hold (Putting Requests On/Off Hold Status) | If the Requirements Analyst is unable to work on any tasks during the New Service Request (NSR) process pending response/follow-up from stakeholders or time constraints, send an email to Cheryl Sklar and Leslie Dagen and ask them to put the NSR on hold. Once approval is received, enter a comment indicating the status. Any analyst can take a request off of on-hold status by returning the on-hold handoff.
Saving NSRD Tab Changes/Updates | If changes are made to a tab, select "Save Changes" at the bottom of the screen before proceeding to the next tab or closing the browser. Otherwise, your changes will NOT be saved.
Routine/Regular | Designation for an initiative that will follow the general NSR processing steps outlined in this document.
Mandated | Designation for an initiative that is considered mission critical or must-do work due to a business driver, such as a congressional mandate, Food and Drug Administration (FDA)/Joint Commission compliance, Secretary's priority, patient safety recommendation, etc. The mandated request is put on a funding list that will be approved on an annual basis. Funding is applied as it becomes available.
Fast Track | Designation for an initiative that could not wait for implementation due to impending risks. (Refer to the "Fast Track" worksheet tab below for additional details).
Major Initiative | Designation for an initiative that is of the highest priority within the Veterans Health Administration (VHA). NSRs verified as associated with a Major Initiative typically move into the Level 2 (Analysis) phase.
Management Link Versus Public Link - There are two distinct web addresses that can be used to access the NSRD:
(1) Management Link | • Designated for Requirements Analysts to enter updates/changes directly to the NSRD. • More robust than the general public site and contains data used internally to monitor the request's progress. • Any updates made using the NSRD management link will automatically update the basic information contained on the general public version of the website • Contains "nsrdmgmt" in the web address (e.g., http://vista.med.va.gov/nsrdmgmt/Tab_GeneralInfoView.asp?RequestID=########). Note: Change the last eight digits in the link to the NSR # to be reviewed.
(2) Public Link | • An informational site that is designated for users who should not be able to enter updates/changes directly to the NSRD (i.e., requesters, Business Owners). The only exception is the "Field Comments" tab, which provides a means for the "public" to enter comments directly into the NSRD. The field can enter comments at any time, but only comments entered within a specified period will be presented to the Clinical Capability Management Board (CCMB) for their consideration. • Does not contain "nsrdmgmt" in the web address (e.g., http://vista.med.va.gov/nsrd/Tab_GeneralInfoView.asp?RequestID=########). Note: Change the last eight digits in the link to the NSR # to be reviewed. • Should be the link given to stakeholders to review information/updates regarding the NSR.
Option 1: Accessing A Specific Request Within The NSRD (Via The Analyst To Assigned Link)
Utilize the following link to access an NSR that has been assigned to you: NSR Assigned To Analyst
Within the General Status section, select the "number" associated with “active NSRs” to retrieve the list of requests assigned to you.
Select the assigned NSR to be updated.
Note: If the NSR does not appear in the analyst's list of assigned requests within the management tool, search for the request using Option 2 below. Otherwise, continue to the next section (Level 1 [Assessment]).
Option 2: Accessing A Specific Request Within The NSRD (Using An NSRD Management Link)
Utilize the following link to access an NSR: Link
Change the last eight digits in the link to the NSR # assigned.
Select the Stakeholder tab and update the primary Requirements Analyst with your name. (Click on the "Add Stakeholder" button to enter all applicable and mandatory fields. Click on "Add Stakeholder" button again to save your entry. Note: Under the "Add Stakeholder" button, there is an option to return to the "Stakeholders" tab if you wish not to save your entry.) For additional assistance, contact Leslie Dagen.
Option 3: Accessing A Specific Request Within An Analyst Assignment Email Notification
An automated email notification is sent to the Requirements Analyst when s/he is assigned as an analyst for the request.
Click on the link provided to access the request in the NSRD (this will be an NSRD Management link).
General NSRD Guidance
NSR Categories Each NSR falls in one of the following categories. If uncertain, consult with the RDM Lead for guidance.
Accessing the NSRD Each NSR falls in one of the following categories. If uncertain, consult with the RDM Lead for guidance.

## Level 0 (Initiation)
Endorsement
Complete? | Column1 | Description
This phase includes NSR Requester submission of the request into the Innovation and Development Request Portal (IDRP). The NSRD Management Lead verifies endorsement and then accepts the request into the NSRD.
Populating the "Tracking" Tab
Complete? | Column1 | Description
|  | The "Request Received" date is automatically populated when the request is accepted into the NSRD. | See recommendations in blue-LM | Analysts don't complete this prompt. These details are included in the Process Dictionary.
|  | The NSRD Management Lead records the "Endorsement Validated" date. Requirements Analysts are not to change this date without contacting her. | See recommendations in blue-LM | Analysts don't complete this prompt. These details are included in the Process Dictionary.
|  | The NSRD Management Lead populates the "Endorsement Bypassed" check box, if applicable. | See recommendations in blue-LM | Analysts don't complete this prompt. These details are included in the Process Dictionary.
The NSRD Management Lead works with the RDM Lead to assign an analyst to the request.
The "Analyst Assigned Date" prompt is automatically populated when the NSRD Management Lead first identifies the primary requirements analyst for the request.
Level 0 (Initiation Phase)
Note on C6: Note: NSRD Management Lead: Leslie Dagen
Note on C11: Note: NSRD Management Lead: Leslie Dagen
Note on C12: Note: NSRD Management Lead: Leslie Dagen
Note on C13: Note: NSRD Management Lead: Leslie Dagen
Note on C14: Note: NSRD Management Lead: Leslie Dagen

## Level 1 (Assessment)
e Re
Populating the "General Information" NSRD Tab
Complete? | Column1 | Description
| 2 | On the "General Info" tab of the selected NSR in the NSRD, update/verify the following fields. If unknown, complete when discovered.
| 2.1 | • Request Type (Select from options provided via the drop down box)
| 2.2 | • Suggested Fast Track (if applicable, enter date); refer to the "Guidance on Fast Track Requests" section of this guide for additional assistance.
| 2.3 | • Fast Track Confirmed (If applicable, enter date); refer to the "Guidance on Fast Track Requests" section of this guide for additional assistance.
| 2.4 | • Classification (If applicable) - (Select from options provided via the drop down box)
| 2.5 | • Brief Description - This response should be business focused and not solution-based (use information gathered in the "Initial Request" section located on the "Links" tab to help complete this section). Update/correct the description if you obtain information that makes the original text out of date.
| 2.6 | • NSR Type (Select from options provided via the drop down box)
| 2.7 | • Suggested Mandate Type (If applicable); select from options via drop down box ▫ If there is no mandate associated, select “No Mandate” from the drop down options. ▫ If there are multiple mandates, select all that apply. Note: Document additional suggested mandate drivers on the "Comments" tab (designated as an "External" entry), upload links in the Supporting Mandate Documentation field on the "Links" tab, and add links within the Business Requirements Document.
| 2.9 | • Related NSRs (If applicable) – Defined as requests that are related to similar topics, but each request has its own assigned NSR (and subsequently a separate Business Requirements Document [BRD]). When this information is documented in the Initial Assessment Questionnaire, it should auto-populate this prompt.
| 2.1 | • Level 2 Parent/Child NSR (If applicable) – These relationships are appropriate when you do not intend to do separate requirements for the children, because the child requirements will be documented in the parent BRD. In this scenario, the parent request remains open, and the children request(s) should be closed.
| 2.11 | • Application (Select from options provided via the drop down box)
| 3 | Select "Save Updates" before proceeding to another tab.
Populating the "Alignment" NSRD Tab
Complete? | Step | Description
| 4 | Data under the "Initiative List Information" section of the page will be either auto populated or populated by the NSRD Management Lead.
| 4.1 | Under the "Dependencies" section of the page, select all that are applicable. If unknown, complete when discovered.
Populating the "Stakeholders" NSRD Tab
Complete? | Step | Description | Column1
| 5 | On the "Stakeholders" tab of the NSRD, update the following roles/fields (at a minimum) – designating at least one as primary for each category, even if only one name is listed. (Note: To add Stakeholders, click on "Add Stakeholder" button to enter all applicable and mandatory fields. Click on "Add Stakeholder" button again to save your entry. Under the "Add Stakeholder" button, there is an option to return to the "Stakeholder" tab if you wish not to save your entry.)
Note: Some requests involve more than one business area. Be sure to include all relevant stakeholders.
| 5.1 | • Business Owner(s) (If unknown, research the HSIS database. If additional assistance is needed, contact the Lead RA Analyst (if government analyst) or Level 1 Government Reviewers (if contractor). Ensure at least one Business Owner is identified as "primary". HSIS Link - http://go.va.gov/hsis. (Select HSIS, Request username/password from Lead RA Analyst)
| 5.4 | • Subject Matter Expert(s) (If unknown, complete/add when discovered)
| 5.5 | • Technical Analyst (If applicable/available) – If name is not listed within the table, enter as a Subject Matter Expert (SME).
| 5.7 | • Program Office Representative (If applicable/known)
| 5.8 | • Requirements Analyst
Note: The Endorser category should never be modified. If you have questions, contact the NSRD Management Lead.
| 4.9 | • Business Owner Representative (If unknown) - Identify BO; send email to him/her requesting POC (along with time commitment expected) - canned email (to be developed)
Populating the "Tracking" NSRD Tab
Complete? | Step | Description
| 5.3.1 | Ignore the Product Selection Required (If applicable, enter date) field. This field is just used for Class III requests.
| 5.3.2 | Unless the request is already endorsed by the Program Office/Business Owner, enter the date the Program Office/Business Owners are identified date during the Assessment Phase.
Reviewing/Populating the "Comments" NSRD Tab
Complete? | Step | Description
| 5.3.1 | At a minimum, a comment must be entered weekly to provide a status of the NSR throughout Levels 0-3. The comment should include as much detail as possible so if the primary analyst is unavailable, others will be able to follow the progress and understand the current status of the request. Use first and last names of customers always when documenting comments in the NSRD.
When "unusual" circumstances occur with an NSR, the analyst should include as much detail as possible in an external comment within the NSRD. Additional details that would assist RDM Analysts with future analysis work or post-analysis reviews should also be documented (for the same date) as an internal NSRD comment.
Prior to contacting SMEs, review previous NSRD and IDRP comments contained on the Comments Tab of the NSRD to obtain a full understanding of actions that have occurred prior to your assignment.
Identify Appropriate Business Owner(s)
Complete? | Step | Description | Column1
Follow the guidance provided at the following link to identify the appropriate business owner(s).
If unable to identify Business Owner(s) after completing steps above, the RDM Analyst should confer with the NSRD Management Lead and the Lead RA Analyst to confirm the name of the appropriate Business Owner(s).
If necessary, the RDM Analyst is responsible for sending an canned email (link) to the Business Owner(s) to confirm ownership of the request.
Populate Business Owner name(s) on the Stakeholders tab.
Populate the "Program Office Business Owners Identified" prompt on the Tracking tab.
Preliminary Research
| Step | Description
Utilize system test accounts (such as Computerized Patient Record System [CPRS] or Veterans Health Information Systems and Technology Architecture [VistA]) before, during, and/or after the call with the requester to gain familiarity with functionality/problem. If you do not have information on the test account, contact the RDM Director.
| 7.2 | Review the VA Software Documentation Library: http://www.va.gov/vdl/.
| 7.3 | Review Remedy (http://vaww.essremedy.va.gov/) and the CA Service Desk Manager Tool [https://helpdesk.r02.med.va.gov/CAisd/pdmweb.exe].
| 7.4 | Review ongoing development activities in the Technical Services Project Repository (TSPR) (http://tspr.vista.med.va.gov/warboard/portfolio.asp).
Assessment Team Engagement, Initial SME Communication, Request Familiarization
(Complete In 5 Business Days)
| Step | Description
| 6.1 | Identify Members of Assessment Team (includes minimally the requester, Business Owner representative, RDM Analyst)
| 6.2 | Schedule Call/Call Prep: In preparation for the first “official” call with the requester, it may be helpful to send the list of the questions from the RDM Initial Assessment Questionnaire (IAQ) (available on Share Point or via the "Links" Tab) ahead of time. (This depends on when the analyst was assigned and when this communication occurs.) Even though responses to the Questionnaire are not populated until the first call, this will provide insight to the requester/SMEs on information needed in a shorter period of time. CC: The Assessment Team in the email to requester.
| 6.3 | Initial Call With Requester and Assessment Team (Call To Complete Questionnaire): Introduce self/role, review NSR process or what they can expect, share Assessment Phase timeline, obtain a basic understanding of what is being requested, gather any supporting documentation they may possess (e.g. Healthcare Failure Mode and Effect Analysis [HFEMA] reports, Patient Safety incident documents, documents supporting mandates, etc.), query about other people/groups who may be involved with this request, explain importance of additional documentation to be completed by requester and document patient safety issues (if applicable).
| 6.3.1 | Populate responses received during the Initial Assessment call(s) in the "Initial Request" prompt on the Links Tab. If solutions were included or if responses are incomplete/unclear on the initial IDRP responses submitted, update as appropriate within the NSRD. A template which includes the Initial Assessment Questionnaire questions in Microsoft Word format is located at the following link.
| 6.4 | Populate the "Assessment Team Meeting Date" prompt on the Tracking Tab with the date of the Initial Assessment Questionnaire completion call. This action signifies the beginning of the Assessment Phase.
| 6.5 | Continue to work with the Assessment Team (via calls or email) to finalize responses to the Initial Assessment Questionnaire and draft high level epics/business needs in the preliminary Requirements Traceability Matrix (RTM). (Note: Begin to enter the draft epics/business needs into the requirements repository at this time.)
Note: At this point, do not link HIPAA requirements from the NSR in the requirements repository, but leave them in the RTM. They will be addressed during Level 2.
Making Changes To NSR Name/Initial Request Form (IDRP Responses)
| Step | Description
Scenario 1: Review NSR name to ensure the title is an appropriate short descriptor of the business need. If it is not, work with the stakeholders/Business Owners to develop a new name.
Scenario 2: When stakeholders request changes to the NSR name and/or the initial request form (e.g., IDRP responses) ensure the request is in writing and the requester is aware of and approves the proposed changes.
When the new name is accepted by the requester and Business Owner, document the name change on the "Comments" tab and forward email to the RDM Management Lead for corrections, as appropriate.
Trigger for Field Comment Period (Applies Only for Clinical Requests)
| Step | Description
| 6.6 | Once consensus is obtained on the content of the "Initial Assessment Questionnaire", respond to the prompts as appropriate at the bottom of the electronic questionnaire to initiate the Comment/Review Period. Respondents are guaranteed that their feedback will be reviewed if they respond within the 9 calendar day comment period. (Note: The RDM Analyst should continue to assess the request during the comment/review period.)
Environmental Scans (Unfulfilled and Legacy Requirements)
(Complete in 5 Business Days Concurrently With Obtaining/Finalizing Questionnaire Responses)
| Step | Description
Note: The purposes of the environmental scan are to: (1) Determine if the enhancements requested have been requested previously via searches in the Requirements Repository and the NSRD - If the enhancements have been requested previously, review the status of the earlier NSR and work with the Assessment Team and the Lead RA Analyst to document the results. (2) Identify related requirements - If requirements are related, document the NSR number and name associated with these related requirements on the Initial Assessment Questionnaire. IMPORTANT NOTES: - Requirements identified during the environmental scan process should not be rewritten at this time. - The environmental scans outlined below may yield the same results, but only document them once in this RTM. - Complete all preliminary scans first before presenting results to SMEs for review and decision (inclusion in this NSR or not).
Environmental Scan #1 - Unfulfilled Requirements (Requirements Repository)
| 6.5 | The Requirements Repository Team generates a report of unfulfilled business needs/epics and requirements/user narratives from the requirements repository related to the current NSR (based on keywords and/or VistA packages referenced in the initial request) as soon as the "NSR" designation is given. This report is forwarded to the analyst assigned to the request.
| 6.5.1 | Upon receipt of the spreadsheet, review results with SMEs to determine duplicate and related functionality/efforts that are within the NSR scope. (Note: For large lists, consider assigning sections of the requirements to SMEs to review based on expertise.) Begin RTM development for the request.
| 6.5.4 | Share the draft RTM with all Assessment Team.
| 6.5.5 | Save the draft RTM in the NSRD (Links Tab).
Environmental Scan #2 - Unfulfilled Requirements (NSRD - Regular and Class III to Class I NSRs)
The RDM Analyst conducts a search within the NSRD based on keywords and/or VistA packages referenced in the initial request.
As NSRs are identified, analyze the request along with its associated business needs and requirements to determine duplicate and related functionality/efforts that are within the NSR scope.
| 6.5.1 | Review results with SMEs to determine duplicate and related functionality/efforts that are within the NSR scope. (Note: For large lists, consider assigning sections of the requirements to SMEs to review based on expertise.) Begin RTM development for the request.
| 6.5.4 | Share the draft RTM with all Assessment Team.
| 6.5.5 | Save the draft RTM in the NSRD (Links Tab).
Environmental Scan #3 - Unfulfilled Requirements (Health Systems Information Suite [HSIS])
The RDM Analyst conducts a search within the HSIS database based on keywords and/or VistA packages referenced in the initial request. Link to the site: http://go.va.gov/hsis (Request username/password from Lead RA Analyst).
As NSRs are identified, analyze the request along with its associated business needs and requirements to determine duplicate and related functionality/efforts that are within the NSR scope.
| 6.5.1 | Review results with SMEs to determine duplicate and related functionality/efforts that are within the NSR scope. (Note: For large lists, consider assigning sections of the requirements to SMEs to review based on expertise.) Begin RTM development for all the request.
| 6.5.4 | Share the draft RTM with all Assessment Team.
| 6.5.5 | Save the draft RTM in the NSRD (Links Tab).
Environmental Scan #4 - Unfulfilled Requirements (VA Mobile Application Environment [MAE], JIRA, and Wiki)
The RDM Analyst sends the NSR link with a list of keywords to the RDM Mobile Applications Liaison (currently, the only RDM Team Member with access to VA MAE JIRA and Wiki and who will conduct the scan using keywords/search terms provided by the assigned RDM Analyst).
| 6.5.1 | Upon receipt of the spreadsheet/results, review with SMEs to determine duplicate and related functionality/efforts that are within the NSR scope. (Note: For large lists, consider assigning sections of the requirements to SMEs to review based on expertise.) Begin RTM development for all the request.
| 6.5.4 | Share the draft RTM with all Assessment Team.
| 6.5.5 | Save the draft RTM in the NSRD (Links Tab).
Environmental Scan #5 - Unfulfilled Requirements (Innovations and Waivers)
Innovations: Use the following link to access the VHA Innovation Program's eBook, a web-based tool that highlights the Program's many critical health care innovations being developed and piloted throughout the field.
Waivers: Environmental scans are done by individuals within the Open Source Management Team prior to their submission to Innovation and Development Request Portal (IDRP) as a Class III to Class I request.
| 6.5.1 | Upon receipt of the documents/results, review with SMEs to determine duplicate and related functionality/efforts that are within the NSR scope. (Note: For large lists, consider assigning sections of the requirements to SMEs to review based on expertise.) Begin RTM development. for all the request.
| 6.5.4 | Share the draft RTM with all Assessment Team.
| 6.5.5 | Save the draft RTM in the NSRD (Links Tab).
External Workgroup Reviews (If Appropriate)
| Step | Description
| 6.9 | If the request involves consult functionality, send an email to Dr. Michael Davies requesting Consult Workgroup Review of your request.
Additional Stakeholder Contact (Occurs Concurrently with Field Comment Period, but feedback may be received after the period is over)
Complete? | Step | Description
| 6.1 | Based on initial discussions with the requester or previous experiences with similar NSRs, notify pertinent work groups or advisory groups who have already been involved in discussions or reviews, or may need to be involved regarding this enhancement (e.g., Bar Code Medication Administration [BCMA],) and upload documentation of discussions and decisions made by these workgroups in the Supporting Documentation link. (Note: These work groups are primarily advisory in nature and make recommendations.)
| 6.12 | Add an NSRD comment indicating the query to specific workgroup(s) and a summary of the decisions made with a reference to additional documentation in the Supporting Documentation link.
| 6.13 | Add the name of the workgroup and their decision to the "Tracking" tab by selecting the add a review prompt. Use the dropdowns for review group and group decision and then save your entry. You are able to add information on multiple groups. If you have a review by a group that isn't on the dropdown, contact the NSRD Administrator to have that group added.
Complete? | Column2 | Column3 | Column1
Level 1 Review (By Assessment Leads)
Description
All analysts (not just contract staff) must notify Level 1 Government Reviewers that the IAQ, RTM, and NSRD are ready for Level 1 review via email. This does not apply to government analysts if Level 1 and 2 activities are running concurrently.
Note: Refer the NSR Level 1 Needs Entered In DOORS Quality Review Checklist for additional guidance.
Send request to NSRD Management Lead to put the request on hold while this review is being done.
RDM Analyst should remove the hold when the review has been completed.
Field Comment Assessment/Review (Complete in 3 Business Days)
| Step | Description
| 8.4 | At the end of the Field Comment period, populate the "Field Comment Complete Date" prompt on the Tracking tab.
The RDM Analyst will aggregate the field comments using the Microsoft Excel feature, review the comments and, if necessary, have follow-up dialog with the commenter and the Assessment Team/requester to modify or otherwise respond to the field comments. The RDM Analyst may need to modify the Initial Assessment Questionnaire.
Collaborate with the Assessment Team and utilize the Initial Assessment Questionnaire content to update draft high level business needs/epics or user narrative (depending on the complexity of the requested functionality) developed using the RTM template, which should be reviewed with SMEs for concurrence. (Functionality complexity varies by request. Work with Level 1 Government Reviewers to determine the required documentation.)
The RDM Analyst will enter an Assessment Team Outcomes comment (via the Comments tab) summarizing the outcome from the comments received during Field comment period.
Finalize the completed assessment package (Initial Assessment Questionnaire; Initial RTM)
Levels 1 and 2 Running Concurrently (Skip Level 1 and Formal Review Phase, Proceed to Level 2)
|  | Description | Column1
If a decision has been made to skip Level 1 and Formal Review phases and proceed directly to Analysis, enter the date the IAQ is completed as the Assessment Completion date.
The Assessment Decision should be updated to "Review Phase Not Needed".
Levels 1, 2 and 3 Running Concurrently (Skip Levels 1 and 2 and Formal Review Phase, Proceed to Level 3)
Description
If a decision has been made to skip Levels 1, 2, and the Formal Review phase and proceed directly to Level 3, enter the date the IAQ is completed as the Assessment Completion date.
The Assessment Decision should be updated to "Review Phase Not Needed".
The Analyst will not enter a date for Proposed Start or Actual Start under the Level 2 Actions section of the NSRD.
The Analyst must update the "Level 3 Analysis Required" prompt to "Needed".
Once the screen is saved, this combination will trigger the system to update the Level 2 status at the top of the screen to "Not Needed" and the Level 3 status to "Needed".
Submit to Formal Review Phase
| Step | Description
| 9.5 | Populate the "Assessment Complete" and "Assessment Decision" prompts on the Tracking tab.
| 10.7 | Complete the Level One Lessons Learned Document. Complete the "Lessons Learned" assessment (located on the Links tab of the NSRD) and follow the guidance provided to complete and save the exercise. Note: Completion of the "Lessons Learned" assessment is not required for NSRs that have been essentially entered as placeholders for externally developed BRDs.
Note on C23: Note: NSRD Management Lead: Leslie Dagen
Note on C30: Note: Lead RA Analyst: Cheryl Sklar Level 1 Government Reviewers: Darlene Handley, Lauren Hardeen
Note on C35: Note: NSRD Management Lead: Leslie Dagen
Note on C52: Note: NSRD Management Lead: Leslie Dagen Lead RA Analyst: Cheryl Sklar
Note on C59: Note: RDM Director: Linda Hebert
Note on C79: Note: RDM Management Lead: Leslie Dagen
Note on C88: Note: Lead RA Analyst: Cheryl Sklar
Note on C101: Note: Lead RA Analyst: Cheryl Sklar
Note on C107: Note: RDM Mobile Apps Liaison: Lauren Hardeen
Note on C126: Note: NSRD Administrator: Don Wilson
Note on C130: Note: Level 1 Government Reviewers: Darlene Handley Lauren Hardeen
Note on C132: Note: NSRD Management Lead: Leslie Dagen
Note on C139: Note: Level 1 Government Reviewers: Darlene Handley Lauren Hardeen
Level 1 (Assessment Phase)
Goal: 15 Business Days

## Formal Review Phase
e Re
Understanding VHA ID Assignments
Description
Each NSR that makes it to the Formal Review phase is assigned a VHA ID number. The Reporting and Analysis (R&A) Team assigns a VHA ID once the Business Owner approved field is populated under the Review Phase. This number is used by the R&A team to track work throughout the lifecycle. On those rare occasions when a request bypasses the Assessment Phase and proceeds to analysis, the RDM Analyst contacts Leslie Dagen to obtain the VHA ID number.
Note: The VHA ID is needed for the HSIS database, which is used to track IT project activity including funding and PMAS progress. If there is no VHA ID, it is not in their database.
Regardless of whether or not a request is discussed during the Assessment Phase or proceeds to analysis, all requests will be assigned a VHA ID (with the exception of requests that are not approved (i.e., Program Office does not support it).
Obtaining Business Owner Approval
Complete? | Column2 | Description | Column1
Using the email template, contact the Business Owner(s) (cc: Level 1 Government Reviewers) for obtain approval of the Assessment Package.
Save the request for approval email in the Supporting Documentation folder.
Note: RDM Analysts should always document the business owner's response (e.g., at least an email) for any deliverable even if it is just an RTM.
Note: Business Owners are given 30 days to respond from the date the initial email is sent with their approval decision. However, the Contract RDM Analyst is only required to maintain the role of RDM Analyst for 7 days after the initial email was sent. Additional guidance is provided below.
Populate the "Sent to Business Owner for Approval" prompt to indicate the beginning of the Formal Review Phase.
Populate the "Assessment Complete" and "Assessment Decision" prompts on the Tracking tab.
Enter the names of all Business Owners on the Stakeholder Tab of the NSRD, if not completed previously.
If a response is received by the Contract RDM Analyst within 7 days, proceed to "Finalizing Business Owner Approval" and then "Contractor-to-Government RDM Analyst Reassignment".
If a response is not received by the Contract RDM Analyst within 7 days, proceed to "Contractor-to-Government RDM Analyst Reassignment".
The Contract RDM Analyst and/or RDM Analyst must attempt to contact Business Owners at least 3 times (with at least one attempt via phone as well as contacting the Business Owner POC for assistance) within 30 calendar days before accepting/processing a "no response" decision.
|  | Contractor-to-Government RDM Analyst Reassignment (Completed by Contractors) | Contractor to Government Analyst Reassignment (Completed by Contractors)
|  | Description | Description
|  | Requests that were assigned to Contract RDM Analysts during the Level 1 - Assessment will be reassigned to a Government RDM Analyst once they have completed this phase (or 7 days after the Business Owner approval of Level 1 email has been sent) to ensure customers have someone to reach out to for questions, etc. (The only exception is when Contract RDM Analysts are completing a BRD or RED for the request.) | Requests that were assigned to contract analysts during the assessment phase will be reassigned to a Government analyst once they have completed this phase to ensure customers have someone to reach out to for questions, etc. (Exception - - Requests that contractors are completing a BRD or RED for.)
|  | Remove the name of the Contract RDM Analyst from the Stakeholders tab. (Do not simply remove the "primary" designation from the contractor's name and assign it to the Government RDM Analyst. Use the deactivation functionality to remove the contractor's name from the Stakeholder table in the NSRD.) | Remove the name of the contract RDM analyst from the Stakeholders tab. (Do not simply remove the "primary" designation from the contractor's name and assign it to the government analyst. Use the deactivation functionality to remove the contractor's name from the Stakeholder table in the NSRD.)
|  | Assign the Government Analyst as the primary analyst on the Stakeholders tab. (If Level 1 Government Reviewers are not already identified in the Stakeholder tab as a secondary analyst, contact them to inquire about who should be assigned to the request.) | Assign the Government Analyst as the primary analyst on the Stakeholders tab. (If Lauren Hardeen or Darlene Handley are not already identified in the Stakeholder tab as the secondary analyst, contact them to inquire about who should be assigned to the request.)
Finalizing Business Owner Approval
Option #1 - Business Owner(s) Approve, No Changes
Upload the approval decisions (email confirmations) in the Supporting Documentation section of the NSRD ("Links" tab)
Add the date the Business Owner Approval was received on the Tracking tab.
Verify approved high level business needs are in the Requirements Repository (leave repository entries as "in Draft") and perform the appropriate tracings. Generally, Business Needs do not have a priority assigned to them (certainly not during assessment). Only in rare cases will Business Needs be prioritized.
• Refer to the Rational DOORS SharePoint page for additional guidance regarding linking artifacts, relationship types, and other guidance (e.g., completing attributes for various artifacts) for using the requirements repository.
Populate Ready for Review Board prompt.
Option #2 - Business Owner(s) Approve, But With Changes
Upload the approval decisions (email confirmations) in the Supporting Documentation section of the NSRD ("Links" tab)
Discuss changes with Assessment Team, update the Questionnaire and/or RTM (as applicable), and save updated documents to the NSRD.
Verify the approved high level business needs are in the Requirements Repository (leave repository entries as "in Draft") and perform the appropriate tracings. Generally, Business Needs do not have a priority assigned to them (certainly not during assessment). Only in rare cases will Business Needs be prioritized.
• Refer to the Rational DOORS SharePoint page for additional guidance regarding linking artifacts, relationship types, and other guidance (e.g., completing attributes for various artifacts) for using the requirements repository.
Add the date the Business Owner Approval was received on the Tracking tab.
Populate Ready for Review Board prompt.
Option #3 - Business Owner(s) Disapprove
Upload the approval decisions (email confirmations) in the Supporting Documentation section of the NSRD ("Links" tab)
Communicate Business Owner decision to Assessment Team and discuss next steps (which may include writing a final comment and requesting closure to Leslie Dagen). (Refer to the Close NSR worksheet for additional instructions).
Option #4 - Business Owner(s) Do Not Respond
Attempt to contact Business Owners at least 3 times (with at least one attempt via phone as well as contacting the Business Owner POC for assistance) within 30 calendar days before proceeding with this option. If there is no response, enter the current date at the "Business Owner Approval Not Received" prompt.
Verify the approved high level business needs are in the Requirements Repository (leave repository entries as "in Draft") and perform the appropriate tracings. Generally, Business Needs do not have a priority assigned to them (certainly not during assessment). Only in rare cases will Business Needs be prioritized.
• Refer to the Rational DOORS SharePoint page for additional guidance regarding linking artifacts, relationship types, and other guidance (e.g., completing attributes for various artifacts) for using the requirements repository.
Populate Ready for Review Board prompt.
Capability Management Board Review
Complete? | Column2 | Description | Column1
The RDM Analyst may be responsible for presenting NSR information to the CMBs using the same content presented during the Pre-Screening call (including field comment and process models developed).
After CMB presentation, CMB RDM Liaisons (which may or may not be the RDM Analyst assigned to the request) are responsible for entering the following information on the Tracking tab (Ready For Review Board link): Primary CMB; Date of the review; Priority (optional); Score (optional); Person responsible for Follow-up; Category; Follow-up Action; Review Board Disposition (Decision). Edit as appropriate.
CMB RDM Liaisons (which may or may not be the RDM Analyst assigned to the request) must enter the following information on the Tracking tab: Review Board Decision (Date); Review Board Decision (via drop down selections); Primary CMB; Date of the review; Priority (optional); Score (optional); Person responsible for Follow-up; Category; Follow-up Action; Review Board Disposition (Decision). Edit as appropriate.
If RDM Analyst receives an inquiry regarding the status/prioritization of a request, forward the email to the appropriate CMB RDM Liaison to address.
Formal Review Phase
Note on C14: Note: Level 1 Government Reviewers: Darlene Handley Lauren Hardeen
Note on C60: Note: CMB RDM Liaisons: Business CMB - Joletta Maxile Clinical CMB - LeAnn Miller Data Resources and Analytics CMB - Cheryl Sklar Research and Education CMB - Cheryl Sklar
Note on C62: Note: CMB RDM Liaisons: Business CMB (BCMB) - Joletta Maxile Clinical CMB (CCMB) - LeAnn Miller Data Resources and Analytics CMB (DRACMB) - Cheryl Sklar Research and Education CMB (RECMB) - Cheryl Sklar

## Level 2 (Analysis)
Pre-Analysis NSRD Population
Complete? | Column1 | Description
Note: An automated email notification may be sent to the RDM Analyst when the NSR changes from Level 1 to Level 2 in the NSRD.
An automated email notification is sent to the RDM Analyst when s/he is assigned as an Analyst for the request. The RDM Analyst is not required to wait until the email notification is received to begin analysis efforts if notified previously.
Confirm the Phase has changed to "Analysis" in the NSRD after the CMB review decision.
On the "Stakeholders" Tab, add your name as the primary Requirements Analyst (if it has not already been done previously).
On the "Tracking" tab of the NSRD under the 'Level 2 Actions – High Level Analysis' section, add a proposed start date, proposed completion date, and actual start date (which corresponds to the date analysis work begins for the request). If the actual start date has not occurred, update this prompt when active analysis begins (i.e., reaching out to SMEs to schedule the first analysis call or starting research/reviews before writing the BRD).
Note: If a request that was originally not going to proceed to analysis has a change in status and will now have a BRD developed, the “Screening Held” information originally recorded on the "Tracking" tab of the NSRD needs to be changed. The date when the decision was made to proceed to analysis should be used as the “Screening Held” date and select the drop down response of “Proceed with Analysis” within the "Tracking tab. Save your updates.
When the actual start date prompt is populated, a peer reviewer is assigned. Contact the assigned peer reviewer to discuss an agreed upon BRD/RTM communication plan (e.g., determine how the peer review wants to be informed/included for concurrent BRD/RTM reviews).
Refer to the RA Documentation Link tab for additional guidance on requirements documentation and bundling requests.
Preparing For Kick-Off Call
Complete? | Column1 | Description
Review previous NSRD and IDRP comments contained on the Comments Tab of the NSRD to obtain a full understanding of actions that have occurred prior to your assignment.
Ask designated PD liaison for a resource to participate in the initial calls to discuss business requirements and determine feasibility from Office of Information and Technology (OI&T) point of view. (Note: Upon inquiry, a Point of Contact [POC] may not be available from OI&T. This should not stop your analysis efforts.)
Review the field comments and send an email to those with "helpful" comments (or something more than "I like this idea") asking if they would like to serve as a SME for this request.
Include ASD representative(s) on all meeting invitations.
Request for Business Architecture Assistance (Optional): For complex NSRs, ask Business Architecture for process modeling support. For NSRs with low complexity, the RDM Analyst can opt to develop process models. - Submit requests for process model support to Cheryl Sklar (for analysis efforts), who will make a formal request on the RDM Analyst's behalf. - If process models are produced by RDM, save a copy of the version approved by the requester/SMEs to the Supporting Documentation link of the NSRD for availability during the Analysis phase. - If the process models are produced by Business Architecture, select the “Add PMSR Link” option on the Links Tab within the NSRD to populate a link to their database. (Note: Process models developed by Business Architecture are housed in a SharePoint site separate from the NSRD.)
Query requester/key points of contact for additional participants who should be included in the call. (Note: An optional checklist is available to assist in this step.)
Note: If it is determined that BioMed has a role in development of a BRD (and particularly has BRD sign-off responsibilities), engage a representative immediately for early involvement in the process.
The VHA 10P2C HIG NSR Request mail group (Product Development/Health Information Governance) is included in the automated notification that is sent when an NSR begins analysis so they can determine if they may be impacted by this request. If applicable, they will notify the RDM Analyst with the name(s) of representatives who they would like to be engaged in this requirements effort.
Review NSR for other applications that may be impacted by the request. Make sure representatives from these systems are available for the kick-off call.
CPRS Dependencies for Non-Clinical Requests: During Level 2, the RDM Analyst will reach out to RDM CCMB Liaison via email to inform them of potential CPRS dependencies for inclusion in discussions/BRD development activities. Annotate in NSRD (CPRS Dependency). If the project is funded (by the time it is determined a CPRS dependency exists), the analysts assigned to support the CCMB will be contacted via email for inclusion in discussions/elaboration activities.
Schedule meeting at date/time most convenient for participants (make arrangements for unknown participants/callers who may attend the call). Schedule a call via Lync or request a VA Nationwide Teleconferencing System (VANTS) number and/or other teleconferencing/monitor sharing information, and send to participants, including anyone who responds with an interest in being involved (e.g., Health Information Management [HIM], Indian Health Services [IHS]); ask recipients to forward the names of anyone who should also participate so they can be added to the invite.
Send agenda – adding any additional questions/concerns, as needed (an agenda template is located at the following link.
Retrieve a copy of the most recent BRD template from the following link.
Start working on draft BRD (fill in what you can based on documentation in the NSRD, conversations with the requester, etc.).
Save the document to the NSRD with the following file name format: NSR #_NSR Name_BRD. Upload the file in the "Links" tab of the NSRD under "RA Analysis Documentation". Use the draft watermark or other identifier to identify working documents. File name format should remain the same throughout the NSR process. The draft watermark should be used until the documents are ready for Business Owner sign-off. Refer to the "RA Documentation Link" tab for additional guidance.
Retrieve the existing RTM (created during Level 1) from the NSRD and revise epics, user narratives, etc. developed during Level 1, as appropriate. (Update/create additional artifacts in the requirements repository, as appropriate.) (Note: If there is not an RTM, check the requirements repository and use artifacts previously created as a starting point. If no artifacts have been entered previously, create a new RTM.)
Note: If creating a new BRD (refreshing a BRD) for a new NSR using requirements from a previous NSR written in the old syntax, add an explanation/sequence of events in Overview Section minimally.
Note: If adding new requirements to an existing BRD, add an explanation/sequence of events in the Overview Section, update the Revision Table, add byline to cover sheet (Updated Month/Year) under previous date, and include change details on the ARAP cover sheet.
Note: If reusing requirements (e.g., from BRDs previously completed), reuse requirements using the old syntax.
• Refer to the Rational DOORS SharePoint page for additional guidance regarding linking artifacts, relationship types, and other guidance (e.g., completing attributes for various artifacts) for using the requirements repository.
Note: Generally, Business Needs do not have a priority assigned to them. Only in rare cases will Business Needs be prioritized.
Draft "as is" and "to be" process model(s) in Business Process Model and Notation (BPMN) format using the Microsoft Visio tool. Send process model(s) (which should be embedded in the BRD) to the requester and other SMEs for review. Process models should include details about the business process rather than the functional level and should be mapped to user narratives in the RTM, where applicable. (Note: If opting to send process models for review in a document separate from the BRD, outputs should be converted to a Microsoft Word or PDF format because not all recipients have access to Visio. )
• Any process models that support the BRD but were created in programs that don’t allow/support inserting the document as an object or copying/pasting the model into different software (i.e. Microsoft Word) will also be placed in this zip folder.
• Before adding new documents to the compressed/zip folder previously uploaded to the NSRD, save it to the network drive - - not the remote desktop. Then, add new documents. Once the new documents have been added, upload the "updated" compressed folder back to the NSRD within the "Links" tab.
Environmental Scan (As Is Requirements)
| Column1 | Description
Environmental Scan - As-Is VistA Legacy Requirements (Necessary Only If Replacing Existing VistA Application)
IF a new system is being created, a comprehensive list of As-Is functionality that is desired in the To-Be state should be developed. (If this request is not for a new system, disregard this section.)
The RDM Analyst contacts Donna Marcum (Donna.Marcum@va.gov) to retrieve a list of As-Is VistA Legacy requirements from the As-Is VistA Legacy Requirements Repository based on keywords (and/or VistA applications/packages/files).
Review the NSR and As-Is VistA Legacy Requirements to make an initial determination of in scope/out of scope.
Analyze and recompose the VistA Legacy requirements (as necessary) to ensure each piece of functionality described reads as a high level business requirement/user narrative.
Compile identified business needs and requirements into a spreadsheet.
Upon receipt of the spreadsheet/results (and when appropriate during the analysis phase), review with SMEs to determine duplicate and related functionality/efforts that are within the NSR scope. (Note: For large lists, consider assigning sections of the requirements to SMEs to review based on expertise.) As business needs/requirements (epics/user narratives) are identified, add them to the RTM, as appropriate.
Kick-Off/Follow-Up Calls
Complete? | Column1 | Description
Facilitate “kick off” call.
Record (document) meeting minutes (you can ask a back-up analyst to help with this task). (A sample meeting minute template is located at the following link.
Send meeting minutes to participants (including action items/response deadlines) and ask for corrections.
Upload meeting minutes to NSRD (create a compressed folder, as needed).
Schedule subsequent meetings as needed. Update requirements deliverables (BRD, RTM), as appropriate throughout this phase of the process.
CC: Peer Reviewer on all SME BRD/RTM reviews (to allow the opportunity for continuous feedback, if this is the agreed upon review mechanism).
If SMEs are having problems completing the Service Level Requirements sections of the BRD, contact Tim Lauterbach, Ton Hall, and Chip Snead (AITC) for technical assistance.
Review background materials and the BRD as well as consult with SMEs to identify any business risk issues.
External/Internal Documentation Reviews
Complete? | Column1 | Description
Documentation quality reviews are helpful in improving the quality and upholding standard expectations for business requirements artifacts. Following are the maximum number of days expected for the various reviews: Service Coordination - 10 days; Security - 10 days; Product Development - 10 days; Tech Writer - 3 days; Peer Review - 3 days; Management Review - 5 days; Business Owner Sign-off - 7 days.
For clinical requests, forward a copy of the BRD to Jonathan Nebeker and Murielle Beene (representing CMIO and CNIO) for review and/or comment. (They may or may not comment.)
External Review #1 - Service Reliability
Service Reliability (Non-Functional Requirements) Review: When the majority of the stakeholder group has provided feedback on the non-functional requirements portions of the BRD and the main ideas for other sections of the BRD have been developed, request a review using the Internal Review Tab notification functionality within the NSRD. (Select the radio button for "Service Reliability" and respond to additional prompts (if applicable) to send an email notification to the appropriate mail group.)
Note: When you send the document for reviews (for example, Security and Service Reliability [a.k.a. Service Coordination]) and the expected response time will not allow you to meet your deadline, you should negotiate an acceptable due date.
Enter a comment on the "Comments" tab as well.
When the document is returned, use the appropriate link within the initial email notification to annotate completion of the review within the NSRD. Update the "Reviewed By" name and date fields, as appropriate. Enter a comment on the "Comments" tab as well.
Incorporate suggestions (as appropriate) from Service Reliability (utilizing tracked changes).
Send draft BRD/RTM to requester and stakeholders for review/comment. Schedule follow-up conference calls and/or email communications to SMEs until Service Reliability's recommendations for the non-functional requirements and the remaining sections of the BRD/RTM have been accurately documented.
Note: Continuously update the Analysis Documents zip folder ("Links" Tab) with the BRD/RTM as they are being updated.
Reminder: Before adding new documents to the compressed/zip folder previously uploaded to the NSRD, save it to the local computer. Then, add new documents. Once the new documents have been added, upload the compressed folder back to the NSRD.
External Review #2 - Security
Security Engineering Review: When the majority of the stakeholder group has provided feedback on the requirements and the main ideas for other sections of the BRD have been developed, request a review using the Internal Review Tab notification functionality within the NSRD. (Select the radio button for "Service" and respond to additional prompts (if applicable) to send an email notification to the appropriate mail group.) Enter a comment on the "Comments" tab as well. IF the reviewer sends a form (or "Security Impact Analysis" document) along with their response (High, Medium, or Low), disregard it. No additional actions are needed beyond documenting their response (High, Medium, or Low) in the BRD.
When the document is returned, use the appropriate link within the initial email notification to annotate completion of the review within the NSRD. Update the "Reviewed By" name and date fields, as appropriate. Enter a comment on the "Comments" tab as well.
Incorporate suggestions (as appropriate) from Security (utilizing tracked changes).
Incorporate recommendations as appropriate from Security Engineering.
External Review #3 - Product Development
Product Development Review: When the majority of the stakeholder group has provided feedback on the requirements and main ideas for other sections of the BRD have been developed, request a review using the Internal Review Tab notification functionality within the NSRD. (Select the radio button for "OI&T Review" and respond to additional prompts (if applicable) to send an email notification to the appropriate mail group.)
When the document is returned, use the appropriate link within the initial email notification to annotate completion of the review within the NSRD. Update the "Reviewed By" name and date fields, as appropriate. Enter a comment on the "Comments" tab as well.
Incorporate suggestions (as appropriate) from Product Development (utilizing tracked changes).
Incorporate recommendations as appropriate from Product Development.
Final Stakeholder Review
Final Draft Stakeholders Review: Send final draft of BRD/RTM to requester and stakeholders for final review/comment, if necessary.
Internal RDM Review #1 - RDM Analyst (Optional)
Final Draft RDM Analyst Review (Optional): Send final draft BRD/RTM to another RDM Analyst to review.
Internal RDM Review #2 - Technical Writing
Technical Writing Review: Request a review using the Internal Review Tab notification functionality within the NSRD. (Select the radio button for "Technical Writer Review", respond to additional prompts, and add comments [if applicable] to send an email notification to the appropriate mail group). Enter a comment on the "Comments" tab as well.
The Technical Writer will enter his/her name on the revision history of the BRD.
The Technical Writer will return the document to the RDM Analyst who requested the review.
The Technical Writer will complete the Quality Management Scorecard to monitor and report on the consistency, accuracy, and quality of all identified work products.
When it is returned, the RDM Analyst will enter a comment on the "Comments" tab.
Internal RDM Review #2 - Peer
Peer Review: Request a review using the Internal Review Tab notification functionality within the NSRD. (Select the radio button for "Peer Review", respond to additional prompts, and add comments [if applicable] to send an email notification to the appropriate mail group). Enter a comment on the "Comments" tab as well. Note: If the primary RDM Analyst is already aware of an assigned peer reviewer, make sure to include this information in the comment when requesting a peer review.
The Peer Reviewer will enter his/her name on the revision history of the BRD.
The Peer Reviewer will return the document to the RDM Analyst who requested the peer review and cc the Director and Deputy Director of RDM on the message.
The Peer Reviewer will complete the Quality Management Scorecard to monitor and report on the consistency, accuracy, and quality of all identified work products.
When it is returned, the RDM Analyst will enter a comment on the "Comments" tab.
Make revisions to the BRD, as appropriate. If discussion with the SMEs is required, do not share the entire document as marked-up by the Peer Reviewer. Instead, separately communicate/discuss the feedback provided by the Peer Reviewer with the SMEs. (Note: The peer review process is an “internal” discussion for improvement of our documentation. Feedback to the stakeholders should reflect a united RDM position, intended to improve their deliverable.)
The RDM Analyst will send updated document back to Peer Reviewer to confirm changes that were made based on the Peer Reviewer feedback and also explain in the email the reasons why other comments were not addressed. If there is an extensive divergence in opinions between the RDM Analyst and Peer Reviewer, the RDM Analyst may initiate a one–on-one discussion with the Peer Reviewer until consensus is reached. The RDM Director or RDM Deputy Director will provide feedback during the Management Review.
Internal RDM Review #3 - Management
Management Review: Request a review using the Internal Review Tab notification functionality within the NSRD. (Select the radio button for "Management Review", respond to additional prompts, and add comments [if applicable] to send an email notification to the appropriate mail group). Enter a comment on the "Comments" tab as well.
The Management Reviewer will return the document to the RDM Analyst who requested the review.
When it is returned, enter a comment on the "Comments" tab.
Make revisions to the BRD, as appropriate. If discussion is required, do not share the entire document as marked-up by the Management Reviewer with the SMEs. Instead, separately communicate/discuss the feedback provided by the Management Reviewer with the SMEs.
Send updated document back to the Management Reviewer to confirm that the necessary changes have been made or explain why they were not addressed.
The Management Reviewer will complete the Quality Management Scorecard to monitor and report on the consistency, accuracy, and quality of all identified work products.
After the Management review, remove the “draft” watermark from the BRD and RTM.
Finalizing BRD and RTM Revision History Tables
Description
Delete all previous entries to the Revision History page of the BRD and RTM. An example of the final Revision History table is depicted below:
Note: Approval dates and the names of the approving officials in the Author column should be added to the document once all signatures have been obtained.
To review Quality Management Scorecard results, use the following link and follow the prompts as appropriate.
Obtaining Approvals/Sign-Off
Complete? | Column1 | Description
Follow guidance documented in the Digital Signature Guide for the email template, additional instructions, and the full list of email recipients). Also, send final version of the documents to the requester as a courtesy.
Note: RDM will utilize the RAP Approvals Signature Template to record RAP approval signatures (regardless of inclusion of Business Architecture artifacts).
Note: Requests associated with priority initiatives - The Business Lead signs off on the documents. Also, send the documents to the OI&T Project Manager for review/sign-off.
On the "Handoffs" tab, select “Initiate Handoff” in NSRD - one to the Program Office and one to Product Development (OI&T), if applicable. For each, add a comment indicating BRD and RTM have been sent for final sign-off.
Requirements and Architecture Package (RAP) Sign-Off Decision Received
Complete? | Column1 | Description
Option #1 - Business Owner Obtained
If sign-off is obtained from the Business Owner for BRD/RTM, update the "Tracking" tab (Complete w/Signed Requirements prompt) of the NSRD with the final approval date (typically the date the last "approver" signed off on the documents).
Update individual approval dates on the Revision History page of the BRD and RTM.
Refer to the Digital Signature Guide for instructions on incorporating approvals in the document and NSRD.
Update the “Handoff Returned” option in NSRD as sign offs occur for each entity. (Refer to the "Communicating with Product Development" section below for additional details about OI&T/Product Development signature.)
Option #2 - Business Owner Sign-Off Not Obtained
If sign-off is not obtained from the Business Owner for BRD/RTM, but documentation is complete, enter date of completion in the NSRD ("Tracking" tab – Complete – No Sign-off). (Note: Before making this decision, discuss with Linda Hebert and Cheryl Sklar. Once you have their concurrence, discuss it with the Requester/Business Owner).
Communicating with OI&T
Complete? | Column1 | Description
RAPs are sent via email to Product Development triage representatives (Roger Sigley, Nancy Meyer, Larry Weldon) to provide an acceptance determination, cc OI&T Project Manager (if known, assigned, and engaged), Linda Hebert, Rose D. Lester, Cheryl Sklar, and Leslie Dagen. Confirm recipients with RA Portfolio Lead.
Placeholder (Pending fleshing out on 12/2/15 BRAMP Call) - Warm handoff - once the PM is determined, the Workgroup will have a call with them to discuss requirements deliverables.
Determine which email template should be used based on the completed requirements deliverables.
If Business Architecture and Information Modelers were involved in the process and provided deliverables, follow guidance documented in the RAP Approvals Signature Template for the email template, additional instructions, and the full list of email recipients. Also, send final version of the documents to the requester as a courtesy.
If Business Architecture and Information Modelers were not involved in the process and did not provide deliverables, follow guidance documented in the Digital Signature Guide for the email template, additional instructions, and the full list of email recipients. Also, send final version of the documents to the requester as a courtesy.
Enter date you send the BRD/RTM to PD in the appropriate area (Technical Assessment Requested From PD - Tracking Tab).
If there is a response (sign off) from OI&T within 14 calendar days, update the date on the Tracking Tab (Technical Analysis Completion - Signed). Also, add a comment to support this action.
If there is no response from OI&T within 14 calendar days, update the date on the Tracking Tab (Technical Analysis Requested - No Sign-Off). Also, add a comment to support this action.
Unfunded NSRs: If the NSR is not funded (or is not anticipated to receive funding in the near future, e.g., within the fiscal year), there is no need to forward the RAP to PD for acceptance.
Post-Analysis NSRD/Requirements Repository Requirements
Complete? | Column1 | Description
Update "Tracking" Tab in NSRD, as appropriate.
Note: Bulk uploads to the repository should only be done by designated analysts (Configuration Manager roles). They are typically only accepted for a large volume of artifacts or for externally generated documentation.
After approval is received (including from the Business Owner), the RDM Analyst will update documentation of business needs/epics, enter business requirements/user narratives, and complete all required "links" between needs/epics, user narratives, requirements (business, non-functional, enterprise, usability), the NSR, the work effort, BFF mappings) into the requirements repository (refer to Rational Tools Training Documentation for additional guidance on the requirements repository). (Note: The requirements repository must be updated with this information within 6 weeks of Business Owner sign-off).
Note: When entering business needs/epics and business requirements/user narratives into the requirements repository, the RDM Analyst should locate the existing NSR artifact. The RDM Analyst should NEVER create duplicate NSR artifacts.
Note: These could have been entered throughout the requirements elicitation process, but the final versions should be documented. At this point, the status for all needs and owner requirements should equal “Approved” and enter a date for “Date Approved”.
Note: Refer the NSR Level 2 BRD Signed Date Populated DOORS Review Checklist for additional guidance.
On the "Tracking" tab of the NSRD, verify the check the box under Level 1 Actions indicating “NEED/Epic Populated in Requirements Repository” is checked.
Enter a comment on the "Comments" tab in the NSRD indicating the date the needs and requirements were added into the requirements repository.
Complete Lessons Learned
Complete? | Column1 | Description
Complete the NSR Post-Analysis Review Lessons Learned using the link at the top of the Links tab in the NSRD. Additional guidance is located on the Lessons Learned worksheet.
Cross Project Linking In Requirements Repository
Description
When the Project Team is ready to proceed with the effort, they will reach out to the RDM Analyst involved to obtain access to existing requirements artifacts in the repository. They need to work together to complete the cross project linking process. Refer to the Cross Project Linking Guide for additional instruction.
Level 2 (Analysis Phase)
Goal: 30/60/90 Days (Depending on Complexity)
Note on C28: Note: RDM CCMB Liaison: LeAnn Miller
Note on C97: Note: Technical Writer: Jennifer Hamm
Note on C98: Note: Note: Technical Writer: Jennifer Hamm
Note on C99: Note: Note: Technical Writer: Jennifer Hamm
Note on C109: Note: RDM Director: Linda Hebert RDM Deputy Director: Rose Lester
Note on C158: Note: Sent follow-up message to Emily to remember what this is.
Note on C170: Note: Configuration Managers: Dirk Hancock Don Wilson

## Repository Tips-Tricks
Have More Recommendations?
Description
If you have additional suggestions for inclusion to this "Repository Tips and Tricks" worksheet, enter them using the embedded link.
General
Description
Font style and size for all artifacts entered should "Arial 10".
When documenting epics/sub-epics and other requirements artifacts, do not use special characters (e.g., &, *, #, etc.).
Clean up (remove) carriage returns in the requirements repository. These are not acceptable formats in the requirements repository, particularly when the content is imported into the NSRD. This can cause truncation during the import process.
VIP
Description
VIP Epics should be entered in paragraph format in the requirements repository. Remove carriage returns used in BRD and RTM templates.
Terms typically displayed in bold (i.e., For, Who, That, Unlike, Our Solution) should be reformatted to "regular" text within the repository.
VIP Artifact Naming Guidance
Description
Utilize the table below to enter requirements artifacts into the repository. (This practice should continue until the new artifact types for VIP have been incorporated in the repository.)
| Artifact Type | Artifact Type In Tool | Tag To Attach
| Epic | Business Need | VIP Epic
| Sub-Epic | User Narrative | VIP Sub-Epic
| User Story | Business Use Case Description | User Story
| Acceptance Criteria | Business Detailed Requirement | Acceptance Criteria
Externally Generated Artifacts
Description
When entering artifacts for externally generated BRDs, they should be entered under "Externally Generated" folder.
Add the "Externally Generated" tag to each artifact.
For additional guidance, reference the appropriate "External BRDs" worksheets within this document.
- External BRDs (with RDM Help)
- External BRDs (without RDM Help)
Requirements Repository Tips & Tricks

## RA Documentation Link
. | Description
Only the most current requirements document should be attached to the RA Analysis Documentation link. Review the following scenarios to determine how documents should be saved to the NSRD:
1 | For older NSRs with only one requirements document (i.e., a BRD) attached to the RA Analysis Documentation link:
o No changes are required unless you are asked to develop a BRCD or a new BRD.
o If/when you are asked to create an additional BRD/BRCD, follow Step 4 below.
2 | For older NSRs with a zip/compressed file containing BRDs/BRCDs attached to the RA Analysis Documentation Link:
o Do not rename the zip/compressed file that is saved to the RA Analysis Documentation Link. The “new” document must replace the “old” documents in this compressed file.
o Download, rename, and save the “old” document(s) to an accessible location on your computer. Use the following syntax to rename the older BRDs/BRCDs: “<NSR Number>_<Name of Request>_<Acronym for Document Type>_<(Month Year Version Completed)>
(Example: “NSR 20150101_Fix This Issue_BRD_(June 2013)” or “NSR 20150101_Fix This Issue_BRCD_(December 2013)”).
o Save the older BRDs/BRCDs in the existing compressed file located in the Supporting Documentation Link.
o Add a hyperlink in the References Appendix of the current/newest BRD/BRCD to the original BRD (which is the Supporting Documentation link).
3 | For NSRs with nothing attached to the RA Analysis Documentation Link:
o Create a zip/compressed folder to save your requirements documents.
* Use the following syntax to name your zip/compressed folder:
“<NSR Number>_<Name of Request>_<Requirements Documents>” (Example: “NSR 20150101_Fix This Issue_Requirements Documents”).
o Use the following syntax to name your file/requirements document:
“<NSR Number>_<Name of Request>_<Acronym for Document Type>” (Example: “NSR 20150101_Fix This Issue_BRD”).
o Save the BRD in the zip/compressed folder.
o Upload the compressed folder to the RA Analysis Documentation Link.
4 | For NSRs that require an additional BRD or BRCD with only one requirements document attached to the RA Analysis Documentation link:
o Create a zip/compressed folder to save your requirements documents.
* Use the following syntax to name your zip/compressed folder:
“<NSR Number>_<Name of Request>_<Requirements Documents>” (Example: “NSR 20150101_Fix This Issue_Requirements Documents”).
o Download, rename, and save the “old” documents to an accessible location on your computer. Use the following syntax to rename the older BRDs/BRCDs: “<NSR Number>_<Name of Request>_<Acronym for Document Type>_<(Month Year Version Completed)>”
(Example: “NSR 20150101_Fix This Issue_BRD_(June 2013)” or “NSR 20150101_Fix This Issue_BRCD_(December 2013)”).
o Save the older BRDs/BRCDs in the existing compressed file located in the Supporting Documentation Link.
o Add a link in the References Appendix of the current/newest BRDs/BRCDs to the location of the original BRD/BRCD (which is the Supporting Documentation link).
o Save the most recent requirements document to the RA Analysis Documentation zip/compressed folder.
o Upload the compressed folder to the RA Analysis Documentation Link.
For NSRs that do not require a "new" BRD; the existing BRD will be updated:
o Revise the existing BRD.
o Save revisions using existing file folder/name set-up.
Requirements Artifacts for Bundled NSRs
o When child NSR is bundled into parent, insert the following text on the first page of the BRD and RTM: Requirements for this request have been incorporated into NSR <insert parent request ID>. Please use the requirements saved to NSR <insert parent request ID> instead of the requirements included in this deliverable.
Saving Documents To the RA Analysis Documentation Link

## Change Mgmt Process
Complete? | Step | Description
Change Requests are initiated via the NSRD and may come from the BO, OI&T, IPTs, and Governance Bodies.
Once a change request is entered, an automated email is sent to the person making the request and the Lead RDM analyst.
The Lead RDM Analyst contacts the primary RDM Analyst to validate.
Once validated, the RDM Analyst will engage the Work Effort Team (including the Lead RDM Analyst) to review the request and determine if the request is in scope for the work effort and/or IT project. (Note: During elaboration efforts, the OI&T PD PM will also be engaged in these discussions.)
Out of Scope Change Requests
For change requests that are out of scope, the Work Effort Analyst Team will advise the requestor to submit an additional New Service Request (NSR). Upon submission of the NSR, a RDM Analyst will be assigned and the request will follow the standard process.
The RDM Analyst will access the change request via the NSRD Management site to enter a status of Rejected as well as the rationale (for example, change requested is out of scope and a new NSR will be entered).
In Scope Change Requests
For change requests that are within scope, the Work Effort Analyst Team will work with the Lead SME/Business Owner and subject matter experts to analyze the change request.
• Reject In Scope Change Request
If the Work Effort Team rejects the change request, justification will be documented in the NSRD and the status of the change request will be updated via the NSRD Management site. (A change request may be rejected due to, but not limited to, funding, lack of resources, project timeline or feasibility.)
• Approve In Scope Change Request
If the Work Effort Team approves the change request, justification will be documented in the NSRD and the status of the change request will be updated via the NSRD Management site.
The RDM (and BA, if applicable) Analyst will make all necessary updates to the appropriate business requirements and architecture artifacts.
Note: Add an explanation/sequence of events in the Overview Section, update the Revision Table, add byline to cover sheet (Updated Month/Year) under previous date, and include change details on the ARAP cover sheet.
Note: If reusing requirements (e.g., from BRDs previously completed), reuse requirements using the old syntax.
Note: New needs/requirements (epics/user narratives) can be created using either the new (epic/user narrative) or old (business need/requirements) syntax.
A summary of the changes will be included in the Approvals Document (ARAP Cover Sheet) and submitted to the Business Owner or Lead SME for approval.
Upon receipt of business approval of the updated artifacts, the updated RAP and Approvals Document will be sent to OI&T Product Development Project Manager.
Save the "new" RAP in the appropriate fields on the Links tab (i.e., Approved/Accepted Documentation section and Business Requirements Sections). The "old" RAP should be saved in the Supporting Documentation folder in the NSRD. Refer to the Documentation Management Guide for additional instruction.
Refreshing Unmet/Partially Developed Requirements
Currently, the Requirements Traceability Team reviews NSRs to identify met versus unmet requirements (including those that were partially developed).
Those that are unmet and partially developed are placed into a new NSR and RTM to document these outliers.
Analysts should always get business owner sign-off (e.g., at least an email) for any deliverable even if it is just an RTM.
Change Management Process
The Change Management Process is utilized when there is a request from an Integrated Project Team or responsible business owner to document changes in an original approved business requirements document (BRD).
• The RDM Analyst will work with OI&T and the business owner to determine if the BRD should be updated or if another document will be used to capture
the changes.
• If they don't agree that the new needs/requirements are in scope, a new NSR (and BRD) is required.
The process for completing this document is similar to that required in completing a BRD, including updating the requirements repository and NSRD. However, there is no requirement to request technical, peer, and management reviews of the updated documents.

## External BRDs (With RDM Help)
Complete? | Step | Description
| D-1 | Confirm the Program Office will be writing the BRD for an NSR.
| D-2 | Enter a comment on the Comments tab of the NSRD of this confirmation.
| D-3 | VHA IDs - Each NSR is assigned a VHA ID number. The Reporting and Analysis (R&A) team typically assigns a VHA ID once the Business Owner approved field is populated under the Review Phase. This number is used by the R&A team to track work throughout the lifecycle. On those rare occasions when a request bypasses the Assessment Phase and proceeds to analysis (such as the case for externally generated BRDs), the RDM Analyst contacts the NSRD Management Lead to obtain the VHA ID number.
Note: The VHA ID is needed for the HSIS database, which is used to track IT project activity including funding and PMAS progress. If there is no VHA ID, it is not in their database.
| D-4 | Work with Program Office to formulate a brief summary of the request.
Note: NSRs with externally generated BRDs only go to the Capability Review Board. (They do not go through Field Comment Review or Business Owner Approval.)
| D-5 | Receive business requirements document (or equivalent) from Program Office.
Note: Documents not created by RDM do not have to undergo the technical writing, peer, or management review process.
| D-6 | Upload supporting documents within the "Links" tab, if applicable.
| D-7 | RDM Analyst reviews the document to ensure it meets the standards for a BRD (correct template used, appropriate content included). If corrections are needed, send recommendations back to the author to update, as appropriate.
| D-7.1 | If process models are included in the externally generated BRD, send email to Tammy Talley [Business Architecture (BA)/Architecture, Strategy, and Design (ASD)] to request support/review.
| D-7.2 | If information models are included in the externally generated BRD, send email to Linda Drummond [Business Architecture (BA)/Architecture, Strategy, and Design (ASD)] to request support/review.
| D-7.3 | Updates RDM section of Stakeholders Table to read - - Did not author this document, but was responsible for working with all stakeholders to ensure the business requirements have been accurately recorded for this request.
| D-7.4 | RDM Analyst verifies the non-functional requirements and security assessment responses have been completed per documentation standards.
| D-7.5 | If non-functional requirements have not been completed or reviewed, work with the SMEs to document the non-functional requirements.
| D-8 | Send the document to Service Reliability (VA 005F Service Coordination SRM Team mail group: mailto: VA005FServiceCoordinationSRMTeam@va.gov) and Security Engineering (VHA OI SDD CASE Services; Susan Nelson (SLC) [mailto:Susan.Nelson3@va.gov]) for review.
| D.8.1 | Enter review requests on the "Internal" tab of the NSRD for each type of review. Enter a comment on the "Comments" tab as well. When reviews are returned, return to the "Internal" tab to enter a completion date. Enter a comment on the "Comments" tab as well regarding the return.
| D-8.2 | Share recommendations from the Service Reliability and Security Engineering representatives with the SMEs for review/input/revisions, as needed.
| D-9 | RDM Analyst inquires if the document has been approved by the Business Owner(s) and OI&T PM. If previously approved, request "approval confirmation messages" (proof from the SMEs/POCs that documents were approved).
| D-9.1 | If approvals have not been obtained, RDM circulates artifacts (BRD and RTM) for approval or assists Program Office/Business Owner with circulation of artifacts.
| D-9.2 | Follow guidance documented in the Digital Signature Guide for the email template, additional instructions, and the full list of email recipients). Also, send final version of the documents to the requester as a courtesy.
Note: RDM will utilize the RAP Approvals Signature Template to record RAP approval signatures (regardless of inclusion of Business Architecture artifacts).
| D-10 | Upon receiving approval from the Business Owner, upload business requirements documents to NSRD on the "Links" tab (Externally Generated Requirements Artifacts).
| D-11 | Enter business needs/epics, business requirements, non-functional requirements, and enterprise requirements into the requirements repository and trace/map/tag (with the "externally generated" tag) appropriately (if the request impacts the VA). For additional information, refer to the following link: http://go.va.gov/ylmd.
Note: When entering business needs/epics and business requirements/user narratives into the requirements repository, the RDM Analyst should locate the NSR record (which is auto-generated in the requirements repository from the NSRD entry). The RDM Analyst should NEVER manually create an NSR record. If no NSR record exists, the RDM Analyst should contact the RDM Requirements Repository Leads.
| D-12 | Completion of Lessons Learned IS required for externally generated BRDs, primarily to ensure documentation requirements within the NSRD and requirements repository have been satisfied.
Populating the NSRD (Tracking Tab)
Use the following "milestones" for populating prompts on the Tracking Tab of the NSRD:
- Program Office Business Owners Identified: Use same date when it was discovered an externally generated BRD would be generated.
- Assessment Team Meeting Date: Use date received the first draft of the BRD from the Program Office.
- Assessment Complete: Use date received the first draft of the BRD from the Program Office.
- Assessment Decision: Change to Proceed to Review Phase. ALL NSRs regardless of whether the BRD is RDM or externally generated, go through CMB review.
- High Level Business Requirements Repository Updated: Check Box (if requirements have been added to the repository).
If not done previously, send email to Leslie Dagen to request a VHA ID.
- Ready for Review Board: Use date received the first draft of the BRD from the Program Office.
- Proposed/Actual Start: Use date received the first draft of the BRD from the Program Office.
- Proposed Completion: 90 days after receiving the first draft of the BRD from the Program Office.
Note on C8: Note: NSRD Management Lead: Leslie Dagen
BRDs not Authored/Created by RDM (with RDM Assistance)

## External BRDs(without RDM Help)
Business Owner Responsibilities For Externally Generated BRDs Without RDM Assistance
When the Business Owner opts to facilitate the entire BRD development/sign-off process, the following steps outline their responsibilities:
For a list of RDM responsibilities, scroll down to the next section.
Complete? | Step | Description
| D-1 | Use the latest VHA templates which can be found at the following SharePoint site (https://vaww.vha.esp.va.gov/sites/RDM/RDM%20Templates/default.aspx) o Business Requirements Document (BRD) Template o Requirements Traceability Matrix (RTM) Template (if applicable)
| D-2 | Create an Innovation and Development Request Portal (IDRP)/New Service Request (NSR) entry for VHA tracking purposes and to accommodate the storage of BRDs and RTMs in the NSR Database for all IT enhancement requests.
| D-3 | Ensure all Business Needs (Epics), Business Requirements (User Narratives), Non-Functional Requirements (as appropriate), HIPAA Requirements, and Enterprise Requirements are included. o If an RTM is not completed, then all of these artifact types must be included in the BRD.
| D-4 | Submit the BRD and RTM (if available) to Service Coordination/Reliability and Security for review and follow-up, as necessary – prior to Business Owner sign off. o Mailgroup for Service Coordination/Reliability – VA 005F Service Coordination SRM Team § BRD sections to be completed (minimally) before requesting Service Coordination review – Overview Section; Goals/Objectives Section; high level business needs; high level business requirements; non-functional requirements; Service Level Requirements section o Mailgroup for Security - VHA 10P2 OIA CASE REQUESTS § BRD sections to be Completed (minimally) before requesting Security review – high level business needs; high level business requirements; Enterprise Requirements
| D-5 | Prior to requesting Business Owner approval, submit all requirements artifacts to the assigned RDM Analyst for review.
| D-6 | Facilitate the process of obtaining Business Owner and Product Development (PD) sign-off.
| D-7a | Ensure Requirements Development and Management (RDM) receives all final (Business Owner and PD approved) requirements artifacts for storage in the NSR Database.
| D-7b | This includes the Microsoft Word AND PDF versions of the BRD. (Note: RDM requests the Microsoft Word version of the document to add the unique identification numbers to each business need/requirement as assigned after entry into the requirements repository. After the identifiers are added to the document, the updated document will be forwarded to the Program Office for their official record.)
| D-8 | Ensure PD/Office of Information &Technology (OI&T) receives all final (Business Owner and PD approved) requirements artifacts for next steps.
RDM Responsibilities For Externally Generated BRDs Without RDM Assistance
When the Business Owner opts to facilitate the entire BRD development/sign-off process, the following steps outline the RDM Analyst's responsibilities:
| D-9 | Receive business requirements document (or equivalent) from Program Office.
| D-10 | If process models are included in the externally generated BRD, send email to Tammy Talley [Business Architecture (BA)/Architecture, Strategy, and Design (ASD)] to request support/review.
| D-11 | If information models are included in the externally generated BRD, send email to Linda Drummond [Business Architecture (BA)/Architecture, Strategy, and Design (ASD)] to request support/review.
| D-12 | Upload document(s) to Externally Generated ARAP link in NSRD.
| D-13 | Enter a comment on the Comments tab of the NSRD of receipt of the document(s).
| D-14 | Populate required prompts on NSRD (General Information Tab). These are the same prompts as any other NSR.
| D-15 | If not done previously, send email to the NSRD Management Lead to request a VHA ID.
Populating the NSRD (Tracking Tab)
| D-14 | Use the following "milestones" for populating prompts on the Tracking Tab of the NSRD:
- Program Office Business Owners Identified: Use same date when it was discovered an externally generated BRD would be generated or received (whichever occurred first).
- Assessment Team Meeting Date: Use date received the BRD from the Program Office.
- Assessment Complete: Use date received the BRD from the Program Office.
- Assessment Decision: Change to Proceed to Review Phase. ALL NSRs, regardless of whether the BRD is RDM or externally generated, go through CMB review.
- High Level Business Requirements Repository Updated: Check Box (if requirements have been added to the repository)
- Ready for Review Board: Use date received the first draft of the BRD from the Program Office.
- Proposed/Actual Start: Use date received the first draft of the BRD from the Program Office.
- Proposed Completion: 90 days after receiving the first draft of the BRD from the Program Office.
| D-15 | Enter business needs/epics, business requirements, non-functional requirements, and enterprise requirements into the requirements repository and trace/map/tag (with the "Externally Generated" tag) appropriately (if the request impacts the VA). For additional information, refer to the following link: http://go.va.gov/ylmd.
Note: When entering business needs/epics and business requirements/user narratives into the requirements repository, the RDM Analyst should locate the NSR record (which is auto-generated in the requirements repository from the NSRD entry). The RDM Analyst should NEVER manually create an NSR record. If no NSR record exists, the RDM Analyst should contact the RDM Requirements Repository Leads.
| D-16 | Once the business needs/requirements have been entered into the requirements repository, populate the BRD (and RTM, if applicable) with the unique identifiers. Upload the updated documents to the NSRD. Send copies of the updated documents back to the Program Office (authors) as a courtesy.
| D-17 | Completion of Lessons Learned IS required for externally generated BRDs, primarily to ensure documentation requirements within the NSRD and requirements repository have been satisfied.
BRDs not Authored/Created by RDM (Without RDM Assistance)
Note on C28: Note: NSRD Management Lead: Leslie Dagen

## Pre-BRAMP Rvw By CBOPC
Complete? | Step | Responsible | Process
| 2 | RDM Analyst | Forwards the email to Business Owner POCs
| 3 | CBOPC Business Owner | Conducts a brief review to determine if the NSR should be assigned to them.
| 4 | CBOPC Business Owner | Responds via email to RDM Analyst within 3 business days of receiving the email (to accept/reject ownership of NSR).
| 5 | RDM Analyst | Updates NSRD with with initial Business Owner decision(s).
· Scenario #1: If NSR ownership rejected, then RDM to determine correct Business Owner (return to Step 1).
· Scenario #2: If NSR accepted, but not supported, RDM closes the NSR.
· Scenario #3: If NSR accepted and needs further assessment, continue to next step.
| 6 | CBOPC Business Owner | Conducts internal Program Office level assessment to determine support of the NSR (within 15 business days of receiving initial email in Step 3).
| 7 | CBOPC Business Owner | Notifies RDM Analysts via email with decision.
| 7 |  | · Supports?
– Business Owner develops an external BRD or
– RDM proceeds with BRAMP Process (Level 1)
· Does Not Support?
– RDM closes the NSR
Pre-BRAMP Review By CBOPC
Overview: Business Owner Assesses NSR's Benefits Prior To Level 1 Activities (Assessment Phase)
Trigger: This process is invoked when the CBOPC Business Owner wants to determine the validity of NSRs prior to beginning the BRAMP process.

## Closing NSRs
Complete? | Step | Description
| A-1 | NSRs can be closed for a number of reasons (e.g., Requester chooses to withdraw request, lack of Program Office support, etc.). Before documenting any “official” notice in the NSRD regarding NSR closure, ensure the following:
| A-1.1 | Regardless of why the request is being closed, the decision must be in writing (from the person closing the NSR) and will be included in the Supporting Documentation folder after notifying the requester.
| A-1.2 | If requester is not aware of upcoming NSR closure, discuss the method of notifying the requester of this negative outcome with the Lead RA Analyst (this process varies slightly among NSR categories as well as by request).
| A-2 | Make sure all Hand-Offs have been returned and all fields have been populated, as appropriate. (Hand-offs occur when the RDM Analyst can not continue any work during the Assessment or Analysis phases until a response is received from an other participant. For example, a document has been sent for review to SMEs or a decision is pending.)
| A-3 | Enter a final external comment on the "Comments" tab in the NSRD indicating why the request is being closed.
| A-4 | Send message (including NSR Name, Number, and reason for closure) to the NSRD Management Lead (cc: the Lead RA Analyst). They will complete a review of the tracking record, will follow-up with the RDM Analyst with any questions, and will populate the Request Closure, and Request Closure Reason fields. If the request has been assigned a VHA ID (on the "Internal" tab), Leslie will notify the R&A team of the action via email.
| A-5 | Update the requirements repository by changing the status of the business needs and owner requirements associated with the applicable work effort and NSRs to "inactive". Tracings to Business Function Frameworks (BFFs or ARCHs), non-functional and enterprise requirements are to be removed as well.
How to Close an NSR
Note on C8: Note: Lead RA Analyst: Cheryl Sklar
Note on C11: Note: NSRD Management Lead: Leslie Dagen Lead RA Analyst: Cheryl Sklar

## Fast Track Requests
Suggested Fast Track (Preliminary Stage)
Complete? | Step | Description
| B-1 | Populate ‘Suggested Fast-Track” field in NSRD if recommendation is made to Fast Track request
| B-1.1 | Work with RDM Lead to determine if request has been deemed as a "Confirmed Fast Track" request.
Scenario 1: Status of "Confirmed Fast Track" Rejected
Complete? | Step | Description
| B-2 | Business Owner and PD agree the request should not be confirmed as fast tracked: RDM Analyst contacts the requester regarding the decision, if the requester was aware of the potential fast track designation.
Scenario 2: Status of "Confirmed Fast Track" Undecided
Complete? | Step | Description
| B-3 | Business Owner and PD cannot agree on whether or not the request should be confirmed as fast tracked: Rely on guidance from RDM Management Team for next steps.
Scenario 3: Status of "Confirmed Fast Track" Approved
Complete? | Step | Description
| B-4 | Business Owner and PD agree the request should be confirmed as fast tracked: RDM Analyst contacts PD’s PMO to alert them to the request and engages them in immediate further discussions with the requester/SMEs.
Follow-on Confirmed Fast Track Activities
Complete? | Step | Description
| B-5 | When confirmed by Business Owner and PD Program Management Office (PMO), enter the Fast Track Confirmed date in the "General Info" tab
| B-5.1 | Engage all stakeholders including Business Owner, PD, and SMEs immediately for discussions.
| B-5.2 | Contact the RDM Deputy Director/Lead RA Analyst/cc: NSRD Management Lead via email to request an update to the status of 'Fast Track Confirmed' field in the NSRD.
| B-5.3 | Continue analysis work toward obtaining final sign-offs on applicable requirements documents. (Confirm with the RDM Management Team regarding what documents and steps are needed for this unique request.)
| B-5.4 | Documentation other than the BRD and RTM that requires the NSR to be fast tracked as well as information about the business risks of not implementing the requirements immediately should be uploaded in the Supporting Documentation section of the NSRD ("Links" tab) and referenced in the BRD/RTM.
| B-5.5 | RDM Analysts contacts PD’s PMO and representatives to engage in further business requirements gathering discussions regarding the request (including whether or not this work could be included in an active project).
| B-5.6 | Continue to follow guidance provided by RDM Management.
Compressed Schedule
Complete? | Step | Description
| B-6 | Security and Service Reliability review can be completed before the final draft is available when there are time constraints.
| B-7 | For fast tracked requests, begin analysis as soon as possible after request has been submitted.
| B-8 | When you send the document for reviews (for example Security and Service Coordination) and the expected response time will not allow you to meet your deadline, you should negotiate an acceptable due date.
| B-9 | When you have an extremely compressed time schedule, hold multiple calls and adjust the agenda depending on who can attend.
| B-10 | If there is insufficient time for technical writer, peer, and management reviews, make sure that at least management review is completed.
Guidance on Fast Track Requests
There are two Fast Track categories – Suggested Fast Track and Confirmed Fast Track. A Suggested Fast Track status could be recommended by anyone. However, a Confirmed Fast Track status has to be agreed on by Business Owner, and PD.
Note on C28: Note: RDM Deputy Director: Rose Lester Lead RA Analyst: Cheryl Sklar NSRD Management Lead: Leslie Dagen
Note on C29: Note: RDM Management Team: Linda Hebert Rose Lester

## Lessons Learned
Differing/Conflicting Needs/Approaches
Complete? | Step | Description
| E-1 | Business Owner has signed-off, but OI&T refuses (i.e., expresses verbal or written refusal of requirements artifacts submitted) to sign-off on the BRD.
| E-1.1 | Negotiate differences/issues with customer.
| E-1.3 | Elevate the issue to RDM Management.
| E-1.2 | Work with ARIWG to get a resolution (if recommended by RDM Management).
| E-1.4 | It is important to keep details of all actions in the "Comments" tab of the NSRD so that even if the dates on the "Tracking" tab are nebulous, the reader would be able to discern the process and evolution of the NSR in narrative form.
Compressed Schedule
Complete? | Step | Description
| E-2 | Security and Service Reliability review can be completed before the final draft is available when there are time constraints.
| E-2.1 | For fast tracked requests, begin analysis as soon as possible after request has been submitted.
| E-2.2 | When you send the document for reviews (for example, Security and Service Coordination) and the expected response time will not allow you to meet your deadline, you should negotiate an acceptable due date.
| E-2.3 | When you have an extremely compressed time schedule, hold multiple calls and adjust the agenda depending on who can attend.
Collaboration/Communication
Complete? | Step | Description
| E-3 | Identify and engage the appropriate SMEs throughout the process. RDM Analysts, Requester, and other SMEs can help you to identify the correct SMEs. Look at other related requests for suggestions on who to contact.
| E-3.1 | Keep business owner informed throughout the process.
| E-3.2 | Utilize teamwork, perseverance, and patience.
| E-3.3 | It is important to keep customers engaged through continuous follow-up regarding status of the NSR and input on draft business requirements.
| E-3.4 | Make reference to the specific NSR in other discussions you may have with same business SMEs for their other projects.
| E-3.5 | Make sure all participants are "on the same" page by getting agreement on areas such as scope, requirements, timeline, etc.
| E-3.6 | While additional discussion may create a delay in finalizing the BRD, it can be helpful to the process by allowing contributions from SMEs .
| E-3.7 | Be persistent (for example, provide follow-up when needed, contact supporting personnel, use telephone and email contact, NOTE: DO NOT directly contact SES). Elevate issues when appropriate (for example, see item 1).
Mentoring
Complete? | Step | Description
| E-4 | When working with new SMEs/business owners, discuss their expectations with the RDM Mentor/Lead Analyst in order to develop requirements elicitation strategy.
| E-4.1 | When the analyst is not familiar with the application area, collaborate with a SME and/or utilize the VA Software Document Library (http://www.va.gov/vdl/).
Call Strategies
Complete? | Step | Description
| E-5 | With large number of SMEs, hold multiple smaller calls based on area to be discussed.
| E-5.1 | With extremely compressed schedule, hold multiple calls and adjust agenda depending on who can attend.
| E-5.2 | Have discussion with Requester/Business Owner prior to beginning analysis to develop a conference call strategy.
On-Hold
Complete? | Step | Description
| E-6 | RDM Analyst should put requests on hold when the analyst cannot work on the request due to reasons that are outside of the analyst’s control, for example: SMEs are not available, waiting for a response before the request can proceed, and the analyst is assigned to other higher priority work and does not have the resources to work on this request. Contact the Lead RA Analyst and the NSRD Management Lead if you have questions about placing a request on-hold.
| E-6.1 | The analyst cannot place the request on-hold. An email message needs to be sent to the RDM Lead to request the on-hold.
| E-6.2 | Analysts can take the request off of on-hold at any time by returning the hand-off.
Miscellaneous
Complete? | Step | Description
| E-7 | The complexity rating is done by the Lead RA Analyst for all requests when they proceed to L2 (analysis). If the complexity level was not done for L2, the RDM Analyst and RDM Requirements Elaboration Lead will jointly determine the complexity for L3.
| E-8 | The original BRD sign-off date is maintained in the BRD and on the NSRD "Tracking" tab. Additional dates are added to the BRD and NSRD when post sign-off revisions are made to the BRD. Additional dates are documented on the "Tracking" tab of the NSRD when an additional BRD is developed (not to be confused with updating a BRD).
| E-9 | Do not delay requirements analysis process to complete steps that will be done during requirements elaboration efforts when/if the request is funded.
| E-10 | If a Root Cause Analysis (RCA) is available, those results should be incorporated into the analysis.
| E-11 | Completion of Lessons Learned IS required for externally generated BRDs, primarily to ensure documentation requirements within the NSRD and requirements repository have been satisfied.
Appendix D - BRDs not Authored/Created by RDM
Lessons Learned Qualitative Responses
Note on C9: Note: RDM Management Team: Linda Hebert Rose Lester
Note on C32: Note: RDM Mentor: Varies, Optional RDM Lead Analyst: Cheryl Sklar
Note on C43: Note: Lead RA Analyst: Cheryl Sklar NSRD Management Lead: Leslie Dagen
Note on C49: Note: Lead RA Analyst: Cheryl Sklar RDM Requirements Elaboration Lead: David Jung

## Acronyms
Term | Definition
BCMA | Bar Code Medication Administration
BPMN | Business Process Model and Notation
BRD | Business Requirements Document
CMB | Capability Management Board
CPRS | Computerized Patient Record System
FDA | Food and Drug Administration
HFEMA | Healthcare Failure Mode and Effect Analysis
HIM | Health Information Management
HIS | Indian Health Services
HPS | Health Provider Systems
ICD | International Classification of Diseases
IDRP | Innovation and Development Request Portal
IE | Information Exchange
iEHR | integrated Electronic Health Record
IT | Information Technology
NSR | New Service Request
NSRD | New Service Request Database
OI&T | Office of Information and Technology
OWNR | Owner Requirements
PD | Product Development
PMO | Program Management Office
POC | Point of Contact
R&A | Reporting and Analysis
RA | Requirements Analysis
RCA | Root Cause Analysis
RDM | Requirements Development & Management
SME | Subject Matter Expert
TSPR | Technical Services Project Repository
VANTS | VA Nationwide Teleconferencing System
VHA | Veterans Health Administration
VISN | Veterans Integrated Service Network
VistA | Veterans Health Information Systems and Technology Architecture
Appendix F - Acronyms

## Revision History
Date | Version | Description | Author
2016-09-06 | 2.25 | Removed references to Quad creation/development from document. | Hebert, Dagen
2016-03-01 | 2.22 | Removed references to ESM/AIM/Portfolio Analysts from document | Sklar, Dagen, Maxile
2015-03-26 | 2.21 | Updated Levels 0 and 1 and added Formal Review Phase with improved Lean process steps. | Lean Process Improvement Team (Jevec, Dagen, Sklar, Hardeen, Maxile)
2014-12-02 | 2.2 | Updated guidance for requesting RAP approvals | E. Jevec, C. Sklar, J. Maxile
2014-11-03 | 2.19 | Added guidance regarding completing and viewing the Quality Management Scorecard. | Peer/Management Review Work Group
2014-09-22 | 2.18 | • Updated verbiage for RAP approval/acceptance email communications to Business Owners, ESMs, and OI&T Manager • Added guidance on PMSR and IMSR • Updated Screening Call guidance • Updated RDM's role with CMB • Added guidance on when to begin drafting epics | RDM Process Mgmt Work Group
2014-09-10 | 2.17 | • Updated guidance on peer/management reviews • Added guidance for completing environmental scans | • L. Hebert, E. Jevec, C. Hirko, C. Sklar, J. Maxile • RDM Process Mgmt WG
2014-06-25 | 2.16 | Added guidance regarding Screening Call and NSRD Comments to the Externally Generated BRDs tab. | J. Maxile, C. Sklar
5/31/2014 | 2.15 | Added Rose Lester as cc recipient for approval emails for Business Owners and PD | R. Lester
5/8/2014 | 2.14 | Updated guidance regarding submission to Customer Advocate. Added guidance regarding updating the requirements repository when a request is closed because functionality is no longer needed. | C. Sklar, J. Maxile, D. Handley, E. Jevec
2014-04-28 | 2.13 | Added guidance regarding Lessons Learned (Level 1), which is not required for NSRs that have been entered as placeholders for externally developed BRDs. | C. Sklar
2014-04-25 | 2.12 | Added guidance on obtaining OI&T sign-off | L. Hebert, R. Lester, E. Jevec, C. Sklar, J. Maxile
2014-04-07 | 2.11 | Added guidance for adding BRDs/BRCDs to the NSRD; updated references to "Requisite Pro/ReqPro" to "requirements repository"; updated references to "Health Systems" to "AIM"; removed references to the "BIRB" | C. Sklar, J. Maxile, L. Miller
2014-02-26 | 2.1 | Updated guidance on BRCD to copy over existing NF, Usability, and Enterprise requirements into the new document even if no changes were made. | C. Sklar
2014-02-24 | 2.9 | Removed step to contact IT Patient Safety to determine if they have evaluated the issue related to the request. They will contact RDM when there are related NSRs. | L. Hebert, C. Sklar
2014-02-13 | 2.8 | Updated guidance for housing the BRD and subsequent BRCDs in Level 2 and the BRCD tabs. | L. Hebert, RDM Process Management Work Group
2014-02-03 | 2.8 | Updated link for Connected Health (Mobile Applications) on cover page. | J. Maxile, L. Hardeen
2013-01-14 | 2.7 | Updated Level 1 with CMB guidance; updated Level 2 with additional stakeholder queries | L. Hebert
2014-01-15 | 2.6 | Added maximum review days, updated with automated review request process within NSRD (Level 2), added BRD approval email template (Level 2) | RDM Process Management Work Group
2013-12-18 | 2.5 | Updated BPMN related note in Level 2. | RDM Process Management Work Group
2013-12-12 | 2.4 | Updated email link for Service Coordination BRD review. | RDM Process Management Work Group
2013-12-06 | 2.3 | Added links to templates for requesting NSR for screening call and action items. | RDM Process Management Work Group
2013-11-20 | 2.2 | Updated clarification regarding business process models to exclude those included externally generated BRDs; Added hyperlink to ReqPro guidance | RDM Process Management Work Group
2013-11-12 | 2.1 | Added clarification regarding business process models | L. Hebert, C. Sklar, D. Handley, J. Maxile
2013-10-16 | 2 | Final tech writing review on new format of the checklist. Changed name from 'Checklist_for_RAEM_Analysts' to RDM Process Guide | J. Hamm
2013-09-30 | 1.4 | Updated entire document as needed. | RDM Process Management Work Group
2013-07-31 | 1.3 | Moved Document from .doc format to .xls format | J. Hamm
2013-06-19 | 1.24 | Removed ONS/PCS review of requests as that step has been eliminated | C. Sklar
2013-05-21 | 1.23 | Updated references from: • RAEM to RDM and RA, as appropriate. • Communications Lead to Requirements Management Lead | J. Maxile
2013-03-15 | 1.22 | Reiterated importance of not manually adding an NSR record to Requisite Pro. | C. Sklar, E. Jevec
2012-12-13 | 1.21 | Added Lessons Learned Qualitative Responses Appendix. | Quality Management WG
2012-10-18 | 1.2 | Removed references to the Screening Call Record, which is no longer utilized. | C. Sklar
2012-04-09 | 1.19 | • Added process for review by OIA if request is related to CPRS or nursing with no prior Health Informatics Program Office support: • Added note regarding how to add new documents to compressed folders • Added guidance regarding not manually entering NSRs into ReqPro • Changed references from ESM to Health Systems • Added guidance regarding not changing endorser information | RDM Process Management Work Group
2011-11-04 | 1.18 | Added statement about NSR closure. | L. Dagen, C. Sklar
2011-09-13 | 1.17 | • Updated standard verbiage for email communication for document review/approval • Added clarification regarding handling and routing of documents related to Major Initiatives versus non-Major Initiatives (BIRB process references) | C. Sklar, E. Jevec, J. Maxile
2011-08-16 | 1.16 | • Updated document with ICD connections steps • Included guidance on storing BRCDs in ClearCase | C. Sklar, J. Maxile, C. Bowen, L. Dagen, D. Handley, P. Montelongo
2011-07-14 | 1.15 | • Updated ability to indicate multiple mandates, if applicable • Added creation of zip folder to house BRDs/ BRCDs/non-traditional process models • Added guidance regarding review request/ completion dates • Added guidance regarding the Security Engineering/Service Reliability review and reconciliation process • Added BRD sign-off clarification (Business Owner versus MI Lead) • Added standard verbiage for BRD sign-off and technical assessment messages • Added Appendix C – BRCD Process • Added Appendix D – BRDs Not Authored/ Created By RDM • Deleted steps regarding CPRS Clinical Work Group and Dr. Nichol reviews | L. Hebert, C. Sklar, C. Bowen, L. Dagen, D. Handley , J. Maxile, P. Montelongo
2011-06-06 | 1.14 | • Updated Service Coordination mail group and when to forward BRD for their review • Added communication component to the Nursing Informatics Committee once a decision has been made (add needs/owner requirements to repository or proceed to analysis) *Moved/updated the CPRS Clinical Work Group and Dr. Paul Nichol recommendation (from the Assessment Phase to the Analysis Phase) • Added depiction of Revision History table within BRD • Added ClearCase tool use (template retrieval and document versioning) • Added guidance for completing BRCD • Added Major Initiative definition | C. Sklar, P. Montelongo, R. Lester, D. Handley, J. Maxile, P. Montelongo, C. Bowen, L. Dagen
2011-05-04 | 1.13 | • Update to the checklist per Linda/Chris’ directive from Manny and Susan L. to have Service Reliability review our BRDs before sign off once non-functional requirements have been completed. • Added step to reach out to other ESM Portfolio Staff when stakeholders/customers outside the primary portfolio have been included as SMEs to the NSR (during the Assessment and Analysis Phases). Should inquire during the ESM Screening Call as well. | C. Rhodes, L. Hebert
2011-04-18 | 1.12 | Quad Chart should not be “approved” by Business Owner/SME if request is proceeding to Analysis. Process Models developed during the Assessment Phase will be saved to the “Supporting Documentation” link. | C. Sklar
2011-03-04 | 1.11 | Major revisions to RDM Checklist to include updated processes | J. Maxile, C. Bowen, D. Handley, L. Dagen, P. Montelongo, C. Sklar
2009-12-14 | 1.1 | Added circumstances when CPRS Work Group Review is needed. Updated fast track explanation. | E. Jevec, L. Hebert, P. Goyal
2009-12-01 | 1.9 | Updated Patient Safety instructions. Added additional level of peer review for BRD | E. Jevec, L. Hebert
2009-11-09 | 1.8 | Updated Patient Safety instructions, processing NSRs not supported by the Program Office, and added explanation for NSR categories (Routine, Mandated, Fast Track) | R. Lester, L. Hebert, E. Jevec
2009-06-01 | 1.7 | Added guidance on populating Program Office support date and associated dropdown, Technical Analysis Completion field population, and the discontinuance of the On Hold status; added Appendix for “How To Close An NSR” | M. Burdick, D. Morgan, J. Maxile
2009-05-11 | 1.6 | Removed word “New” from title; removed instruction to send CBJ to OED for technical assessment | P. Goyal, M. Burdick
2009-04-20 | 1.5 | Moved endorsement instruction to appropriate phase; updated PS Review content; moved Quad Chart completion to appropriate phase; removed “FY” from CBJ and Screening Call Record document names | M. Burdick, D. Morgan, J. Maxile
2009-01-08 | 1.4 | Added guidance on completing analyst portion of NSRD, patient safety determination, and obtained technical assessments | M. Burdick, D. Morgan, J. Maxile
2008-12-31 | 1.3 | OI changed to OHI | J. Hamm
2008-12-04 | 1.2 | Added guidance on pursuing ESM Analyst involvement and uploading CBJ | R. Lester, M. Burdick
2008-11-25 | 1.1 | Changes to CBJ/Quad Review section (guidance for no CBJ response) | M. Burdick, L. Hebert
2008-11-20 | 1 | Initial draft | M. Burdick, A. Glenn, J. Maxile, D. Morgan
Appendix G - Revision History